## Dev Tracker
|  |  | Sprint | 2
|  |  | Days Outstanding | -46065
Sprint | Ticket ID | Type | Title | Description | Priority | Created Date | Status | Dependency (Ticket ID) | Assigned To | End Date | Inital Est. Hours
1 | TMA-000 | Task | *Hide "Cook with Taist" option, "Contact Taist" option, AND Search field on Customer side | Tech Ref | High | 2025-10-29 | STAGING |  | Billy | 2025-12-08 | 1
1 | TMA-001 | Task | Twilio text notifications | Tech Ref | High | 2025-10-29 | STAGING |  | Billy | 2025-12-08 | 5
1 | TMA-002 | Task | Only require phone number + email when signing up as a customer | Tech Ref | High | 2025-10-29 | STAGING |  | Billy | 2025-12-08 | 2
1 | TMA-003 | Task | Cart icon at top of Customer screen | Tech Ref | High | 2025-10-29 | STAGING |  | Billy | 2025-12-08 | 5
1 | TMA-004 | Task | *Simple tutorial overhaul (pictures, make it look nicer, make sure chefs don't skip it) | Tech Ref | High | 2025-10-29 | STAGING |  | Billy | 2025-12-08 | 5
1 | TMA-005 | Task | *Overall styling overhaul | Tech Ref | High | 2025-10-29 | In Progress |  | Billy | 2025-12-08 | 4
1 | TMA-006 | Task | *Simplify chef stripe signup without moving to app | Tech Ref | High | 2025-10-29 | STAGING |  | Billy | 2025-12-08 | 4
1 | TMA-007 | Task | Coupon code functionality | Tech Ref | Medium | 2025-10-29 | STAGING |  | Billy | 2025-12-08 | 8
1 | TMA-008 | Task | **Overhaul entire chef signup flow (not 1 long form, prepopulate stuff if available, address auto finish) | Tech Ref | High | 2025-10-29 | STAGING |  | Billy | 2025-12-08 | 8
1 | TMA-009 | Task | *AI for menu page | Tech Ref | High | 2025-10-29 | STAGING |  | Billy | 2025-12-08 | 8
1 | TMA-010 | Task | Move from AWS to Railway | Tech Ref | Medium | 2025-10-29 | STAGING |  | Billy | 2025-12-08 | 8
1 | TMA-011 | Task | **Calendar overhaul | Tech Ref | High | 2025-10-29 | STAGING |  | Billy | 2025-12-08 | 8
1 | TMA-012 | Task | Enable camera roll option for chef profile pic | Tech Ref | Medium | 2025-10-29 | STAGING |  | Billy | 2025-12-08 | 0.5
1 | TMA-013 | Task | Show Current Location on Home tab | Tech Ref | Medium | 2025-10-29 | STAGING |  | Billy | 2025-12-08 | 2
1 | TMA-014 | Task | Automatic reload when new zip code is added by Admin | Tech Ref | Low | 2025-10-29 | STAGING |  | Billy | 2025-12-08 | 2
1 | TMA-015 | Task | Dialog box on ‘cancel order’ button in case user accidentally taps it | Tech Ref | Low | 2025-10-29 | STAGING |  | Billy | 2025-12-08 | 1
1 | TMA-016 | Task | Time window for chef accepting order and Stripe logic for full refund if Chef does NOT accept order | Tech Ref | Medium | 2025-10-29 | STAGING |  | Billy | 2025-12-08 | 2
1 | TMA-017 | Task | Backend logic to generate AI-generated reviews for a chef everytime a review is submitted for that chef | Tech Ref | Medium | 2025-10-29 | STAGING |  | Billy | 2025-12-08 | 3
1 | TMA-018 | Bug | Categories (including time of day filters) not functioning | Tech Ref | High | 2025-10-29 | STAGING |  | Billy | 2025-12-08 | 1.5
1 | TMA-019 | Bug | Order receipt for chef doesn’t show added customizations written out | Tech Ref | High | 2025-10-29 | STAGING |  | Billy | 2025-12-08 | 1
1 | TMA-020 | Bug | Closed order status needs to update based on certain user actions (If customer/chef cancels order, order is Closed and no further action can be made. If customer submits review, order is Closed and no further action can be made | Tech Ref | Medium | 2025-10-29 | STAGING |  | Billy | 2025-12-08 | 1.5
1 | TMA-021 | Bug | From Order Date selection, ONLY able to tap back button to return to the current day, if user has the exact DAY OF WEEK selected as is the current day (e.g., today is Wednesday; if looking at next week, user can only tap back button when on Wed, not Tue) | Tech Ref | Medium | 2025-10-29 | STAGING |  | Billy | 2025-12-08 | 0.5
1.5 | TMA-056 | Task | UTC time zone for customer seeing chef availability (ordering for tomorrow) |  | High | 2025-01-08 |  |  | Billy
1.5 | TMA-057 | Bug | Words being cut off on the end (last letter) on Android |  | High | 2025-01-08 | STAGING |  | Billy
1.5 | TMA-058 | Task | On my Way' and 'Order Complete' notification verbiage |  | High | 2025-01-08 | STAGING |  | Billy
1.5 | TMA-059 | Task | Add Menu Item Image |  | Medium | 2025-01-08 | STAGING |  | Billy
1.5 | TMA-060 | Bug | Android keyboard blocks special instructions textbox. Keyboard also blocks chat screen between customer and chef |  | Medium | 2025-01-09 |  |  | Billy
1.5 | TMA-062 | Bug | Order request text message to chef is missing first name of customer |  | High | 2025-01-09 |  |  | Billy
1.5 | TMA-029 | Bug | Android Tip/Review screen verbiage checks |  | High | 2025-01-09 |  |  | Billy
2 | TMA-063 | Task | Regular reminder notifications to order (2pm ish on random weekdays) |  | High | 2026-02-05
2 | TMA-022 | Bug | Profile (bio and hours) not visible from Admin Panel pre activation | Pre-activation | Medium | 2025-11-11
2 | TMA-023 | Task | Remove Serving Size and replace with MOQ (every item serves 1 person to start); except for meal prep items |  | Low | 2025-11-13 |  | TMA-034
2 | TMA-024 | Task | Automatic app updates for users |  | Low | 2025-11-13
2 | TMA-025 | Task | Add Stripe Transaction notifications | https://dashboard.stripe.com/acct_1KWXqKKujvfsOOCM/workbench/webhooks | Medium | 2025-11-22
2 | TMA-026 | Task | Email Campaign Automation | Look into Make.com | High | 2025-12-01
2 | TMA-027 | Task | Switch Review character account from 100 to 200 |  | Medium | 2025-12-02
2 | TMA-028 | Task | Assure all time values in Admin Panel are set to EST (or EDT) |  | Low | 2025-12-03
2 | TMA-037 | Task | Add time blockout logic for before, during, and after already-accepted orders |  | High | 2025-12-04
2 | TMA-038 | Task | Replace onboarding graphics with masks for ones without masks |  | Low | 2025-12-04
2 | TMA-039 | Task | Chef button to notify customer of arrival; "Your chef has arrived." |  | Low | 2025-12-09
2 | TMA-040 | Task | Reminder to Chef to put bag/cooler on floor and wash hands |  | Medium | 2025-12-09
2 | TMA-041 | Task | Create Menu Item flow to start with "Standard? Ideal for customers wanting a dish for that evening" or "Meal Prep? Ideal for customers wanting to reheat over a week" |  | Medium | 2025-12-09
2 | TMA-042 | Task | Chef messaging to avoid frozen ingredients (proteins) when creating menu items |  | Medium | 2025-12-09
2 | TMA-043 | Task | Reminder to Chef to turn off any appliances and wipe down surfaces at the time of the order completion (based on arrival time and completion time) |  | Medium | 2025-12-09
2 | TMA-044 | Task | Reminder to Chef that order should almost be complete | when order is 10 minutes to completion (based on arrival time and completion time) | Low | 2025-12-09
2 | TMA-045 | Task | Alternate time selection field layouts for Android |  | Low | 2025-12-09
2 | TMA-046 | Task | Option for chef to request a New Allergen when creating a menu item |  | Low | 2025-12-10
2 | TMA-047 | Task | "Free parking available?" checkbox on Customer side for Chef |  | Low | 2025-12-11
2 | TMA-048 | Bug | Android Chef Profile Not Erasing After Deleting |  | Medium | 2025-12-17
2 | TMA-049 | Task | Speed/performance | point out specific areas (viewing Chefs Available between dates on Home tab) | Medium | 2025-12-17
2 | TMA-050 | Task | Live updating from Pending to Active Chef UI on Android |  | Medium | 2025-12-17
2 | TMA-051 | Bug | Birthday date field inaccurate for Customers page on STAGING admin panel |  | Low | 2025-12-23
2 | TMA-052 | Task | Link Tip/Review page and other pages in Twilio notification |  | Low | 2025-12-30
2 | TMA-053 | Task | Google signup capability |  | Medium | 2025-01-09
2 | TMA-054 | Task | In-app bug/issue reporting |  | High | 2025-01-09
2 | TMA-055 | Task | SMS notifications for chats between customer and chef |  | High | 2026-01-06
| TMA-061 | Bug | Unable to order from chef for tomorrow (without chef live-overriding) | "Middle ground" solution where customer opens the app to the first day where chefs are confirmed available ? | Medium | 2025-01-09
2 | TMA-030 | Bug | iOS Stripe step asking for Statement Descriptor |  | Medium | 2025-01-09
2 | TMA-031 | Task | Add qty adjustment buttons to Customizations when ordering | Tech Ref | Low | Sprint 1 | Not Started |  |  |  | NA
2 | TMA-032 | Task | Strategy around dealing with Stripe accounts linked to different email than what’s linked to Taist account | Tech Ref | Medium | Sprint 1 | Not Started |  |  |  | 2
2 | TMA-033 | Task | General overhaul of menu item (split form into multiple pages) | Add minimum order qty field for chefs | Medium | Sprint 1 | Not Started |  |  |  | 4
2 | TMA-034 | Task | Category overhaul (allow items to go live with an "Other" category | Tech Ref | Low | Sprint 1 | Not Started |  |  |  | 3
2 | TMA-035 | Task | Demand-gated background checks | Temporarily build off existing zip code logic currently pertaining to only customer signups. Con: cannot build up chef profiles in areas ahead of opening in new market (size of issue dependent on actual leadtime of creating a chef profile) | Low | Sprint 1 | Not Started
2 | TMA-036 | Task | Link Privacy Policy and Terms pages | Nothing currently loads for both | High | 2026-02-09 | Not Started
2 | TMA-037 | Bug | Not able to disable PNs and Location Services upon signup |  | Medium | 2026-02-09 | Not Started
Formulas:
End Date = IF([Sprint]<>"",VLOOKUP([Sprint],Sprints!C:G,3,FALSE),"")

## Comments & Pics
Ticket ID | Comment or Picture | Author | Date
TMA-009 | Example 1: Grilled lemon-garlic chicken (or tofu), turmeric quinoa, roasted rainbow veggies, avocado fan, tahini-lime drizzle, and microgreens Example 2: Chickpea pasta in roasted red pepper cashew cream, sautéed spinach, blistered cherry tomatoes, tomato basil chicken sausage, and garlic herb sourdough Example 3: • Day 1: Blackened salmon, wild rice, grilled asparagus • Day 2: Bison meatballs, sweet potato mash, sautéed kale • Day 3: Sauteed Korean BBQ chicken thighs, broccoli, and jasmine rice | Dayne | 2025-11-12
TMA-022 | CAN see Profile on Admin Panel upon activating the chef | Dayne | 2025-11-13
TMA-005 | Assuring size of text and objects is proportional to device screen Assuring white "flash" box is removed when loading into app | Dayne | 2025-11-13
TMA-022 | https://teamtaist.sharepoint.com/:i:/s/Taist2/IQClpkwtP2YYQaj_rRyCZUFNAbqJhhrWTbYYABngX6kSNUU?e=YicLpL | Dayne | 2025-11-13
TMA-022 | https://teamtaist.sharepoint.com/:i:/s/Taist2/IQDfYV_GLez0QZhNZiFb8w7HAcFgLkVSXghvKsfuaA0ceMc?e=KOGDCM | Dayne | 2025-11-13
TMA-005 | Centering logo and signup/login buttons on Welcome Page Eliminating white-on-white logos
TMA-026 | Using Resend for transactional emails Need to look into marketing (time-based) emails towards customers and chefs | Dayne | 2025-12-09
TMA-008 | Can chef be taken back to Home tab after creating first menu item? | Dayne | 2025-12-09
TMA-006 | Can chef be shown the Home tab (instead of inside Step 4), if not taken directly back to Home tab automatically after completing stripe account | Dayne | 2025-12-09

## Deprioritized
Sprint | Ticket ID | Type | Title | Description | Priority | Created Date | Status | Dependency (Ticket ID) | Assigned To | End Date | Initial Est. Hours
Note on K2: Dayne Arnett: comma-separated if multiple

## Sprints
Sprint # | Start Date | End Date | End Date (Actual) | Total Hours
1 | 2025-10-29 | 2025-12-08 | 2026-02-02 | 81
2 | 2026-02-12

## Users (hidden)
Initials | Name
AA | Dayne
DA | Daryl
BG | Billy
S1 | Sprint 1