## Sprint 2 Task Selection
Instructions: Change "Yes" to "No" in column A to remove items. Totals update automatically.
Include? | # | Ticket | Item | Priority | Hours | Cost ($100/hr)
Yes | 1 | TMA-063 | Weekly Order Reminder Notifications | High | 3
Yes | 2 | TMA-026 | Email Campaign Automation | High | 3
Yes | 3 | TMA-037 | Order Time Blockout Logic | High | 6
Yes | 4 | TMA-054 | In-App Bug & Issue Reporting | High | 4
Yes | 5 | TMA-055 | SMS Notifications for Chat Messages | High | 2
Yes | 6 | TMA-036 | Privacy Policy & Terms of Service Pages | High | 1
HIGH PRIORITY SUBTOTAL
Yes | 7 | TMA-022 | Chef Profile Visibility in Admin (Pre-Activation) | Medium | 1
Yes | 8 | TMA-025 | Stripe Transaction Notifications | Medium | 5
Yes | 9 | TMA-027 | Increase Review Character Limit (100 to 200) | Medium | 0.5
Yes | 10 | TMA-040 | Chef Safety Reminder on Departure | Medium | 0.5
Yes | 11 | TMA-041 | Standard vs. Meal Prep Menu Item Type | Medium | 3
Yes | 12 | TMA-042 | Chef Messaging: Avoid Frozen Ingredients | Medium | 0.5
Yes | 13 | TMA-043 | Chef Cleanup Reminder on Order Completion | Medium | 0.5
Yes | 14 | TMA-048 | Android: Profile Not Clearing After Deletion | Medium | 1
Yes | 15 | TMA-049 | Performance: Chef Availability Loading Speed | Medium | 5
Yes | 16 | TMA-050 | Real-Time Chef Activation Status Update | Medium | 2
Yes | 17 | TMA-053 | Google & Apple Sign-In | Medium | 10
Yes | 18 | TMA-030 | Stripe Statement Descriptor Issue (iOS) | Medium | 1
Yes | 19 | TMA-032 | Stripe Email Mismatch Strategy | Medium | 1
Yes | 20 | TMA-033 | Menu Item Enhancements (MOQ Field) | Medium | 3
Yes | 21 | TMA-061 | Unable to Order from Chef for Tomorrow | Medium | 4
Yes | 22 | TMA-037b | Cannot Decline Permissions During Signup | Medium | 1
MEDIUM PRIORITY SUBTOTAL
Yes | 23 | TMA-023 | Replace Serving Size with MOQ | Low | 2
Yes | 24 | TMA-024 | Automatic App Update Prompts | Low | 2
Yes | 25 | TMA-028 | Admin Panel Timezone Consistency (Eastern) | Low | 1
Yes | 26 | TMA-038 | Update Onboarding Graphics | Low | 0.5
Yes | 27 | TMA-039 | Chef "I've Arrived" Notification Button | Low | 2
Yes | 28 | TMA-044 | Order Completion Time Reminder for Chef | Low | 3
Yes | 29 | TMA-045 | Android Time Selection Layout | Low | 2
Yes | 30 | TMA-046 | Chef: Request a New Allergen | Low | 1
Yes | 31 | TMA-047 | "Free Parking Available?" Checkbox | Low | 1
Yes | 32 | TMA-051 | Birthday Date Display Fix in Admin | Low | 0.5
Yes | 33 | TMA-052 | Deep Links in SMS Notifications | Low | 3
Yes | 34 | TMA-031 | Customization Quantity Buttons | Low | 2
Yes | 35 | TMA-034 | Category Overhaul ("Other" Category) | Low | 1
Yes | 36 | TMA-035 | Demand-Gated Background Checks | Low | 2
LOW PRIORITY SUBTOTAL
SELECTED TOTAL
Rate: $100/hr (80+ hrs) ¦ $110/hr (under 80 hrs) ¦ $200/hr (under 40 hrs)
|  |  | ESTIMATED TIMELINE |  |  | weeks